## Sheet1
Issue Key | Issue Type | Summary | Reporter | Assignee | Status | Created | Updated | Component/s | Sprint | consumed Story Points
MATRIX-83425 | Sub-task | [gPTP] Add feature to create macvlan interface for ecu simulation. | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Implemented | 22-Aug-2024 08:15 | 08-Sep-2024 11:01 | gPTP | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 5
MATRIX-83423 | Story | [TKD] Align tkd service | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Implemented | 20-Aug-2024 15:31 | 11-Sep-2024 14:22 | TKD | MATRIX_24.3.4_W38 | 6.75
MATRIX-83422 | Story | [TKD] align tkd_api | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Implemented | 20-Aug-2024 15:31 | 11-Sep-2024 14:22 | TKD |  | 1
MATRIX-83291 | Bug | [Appium v2] Intermittent Failure When Starting Android Activities | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 09-Aug-2024 09:21 | 12-Aug-2024 08:11 | Appium |  | 0
MATRIX-83290 | Story | [FWK] Study and Evaluation of gRPC Deadlines Implementation for MATRIX Services | wissem.MANSOURI@CELADODC-RSWL.com | Eya.Abdelhedi@celadodc-rswl.com | Implemented | 09-Aug-2024 08:32 | 11-Sep-2024 14:58 | Framework |  | 3.5
MATRIX-83229 | Epic | [TKD] Align TKD with Matrix services | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Implemented | 08-Aug-2024 08:19 | 11-Sep-2024 14:22 | TKD |  | 5.75
MATRIX-83228 | Story | [SOME/IP - SDV] use same json format as vsomeip library for E2E Profile 4 | laurent.josse@ampere.cars | wissem.MANSOURI@CELADODC-RSWL.com | Implemented | 08-Aug-2024 07:03 | 13-Sep-2024 09:59 | Canakin | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 7.75
MATRIX-83227 | Story | [SOME/IP - SDV] Implement E2E Profile 4 to be compatible with vsomeip library | laurent.josse@ampere.cars | wissem.MANSOURI@CELADODC-RSWL.com | Implemented | 08-Aug-2024 06:40 | 10-Sep-2024 15:02 | Canakin | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 4
MATRIX-83220 | Story | [AudioFeature.py] While Executing facing $ Detected Text issue | petiti-venkata.sai-manideep-extern@rntbci.com | petiti-venkata.sai-manideep-extern@rntbci.com | Closed | 05-Aug-2024 11:14 | 26-Aug-2024 08:15 | TKD |  | 0
MATRIX-83217 | Story | Move all MATRIX APIs to poetry 1.8.2 | alexandru-rudi.matau@ampere.cars | rahma.haddar@celadodc-rswl.com | Integrated | 05-Aug-2024 09:45 | 05-Sep-2024 12:42 | Services |  | 1.5
MATRIX-83082 | Sub-task | [Token Handler] Fix smartphone_test_service token configuration issue | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 02-Aug-2024 16:05 | 02-Aug-2024 21:16 | Smartphone | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-83081 | Sub-task | [Androsmart Refactoring] Review and Clean-up Client side | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Closed | 02-Aug-2024 15:55 | 19-Aug-2024 08:27 | Androsmart | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 5
MATRIX-83080 | Sub-task | [Androsmart Refactoring] Review and Clean-up on Server side | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Closed | 02-Aug-2024 15:55 | 19-Aug-2024 08:27 | Androsmart | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 5.5
MATRIX-83079 | Story | [Androsmart Refactoring] Review and Clean-up: gRPC Error Code Implementation | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Closed | 02-Aug-2024 15:54 | 26-Aug-2024 08:15 | Androsmart | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 5
MATRIX-83073 | Sub-task | [Token Handler] update_check_should not aborted container execution | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 01-Aug-2024 14:56 | 01-Aug-2024 15:57 | Framework | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-83066 | Sub-task | [Token Handler] Execute check_update_config on matrix as entrypoint | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 01-Aug-2024 10:42 | 01-Aug-2024 10:46 | Framework | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-83065 | Sub-task | [Token Handler] Add check/update config function | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 01-Aug-2024 09:29 | 01-Aug-2024 09:32 | Framework | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-83064 | Sub-task | [Token Handler] Fix Update config cmd on jfrog | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 01-Aug-2024 09:26 | 01-Aug-2024 09:30 | Framework | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-83063 | Sub-task | [Token Handler] Fix jfrog and poetry TLS configuration | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 01-Aug-2024 09:23 | 01-Aug-2024 09:33 | Framework | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-82677 | Story | [Token Handler] Enhance Token Configuration for JFrog and Poetry in MATRIX Service | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | In Progress | 29-Jul-2024 14:31 | 12-Sep-2024 11:21 | Framework | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 15
MATRIX-82674 | Bug | [Matrix] Create a pipeline to validate the draft matrix and the new version of Appium 2 | ahlem.zouaoui@celadodc-rswl.com | Hayet.TAYECHI@celadodc-rswl.com | Closed | 29-Jul-2024 09:56 | 23-Aug-2024 10:53 | Appium |  | 0
MATRIX-82673 | Bug | [SAT][MM][AccessDA/FULLDOM]Pipeline not excuted [need To update Token for Matrix 10.5.4] | Hayet.TAYECHI@celadodc-rswl.com | Hayet.TAYECHI@celadodc-rswl.com | Closed | 29-Jul-2024 09:49 | 19-Aug-2024 09:02 | SAT | SAT_24.3.2_W32 | 0
MATRIX-82672 | Story | Taking more than 40 secs while taping on a element available in the media player | ashrin.femina-extern@rntbci.com | ashrin.femina-extern@rntbci.com | In Progress | 29-Jul-2024 04:59 | 13-Sep-2024 07:52 | Appium |  | 5
MATRIX-82667 | Bug | [Robustness][APPIUM]Failed to start smartphone activity | ahlem.zouaoui@celadodc-rswl.com | ahlem.zouaoui@celadodc-rswl.com | Integrated | 24-Jul-2024 09:04 | 10-Sep-2024 09:15 | Appium | MATRIX_24.3.3_W35 | 0
MATRIX-82661 | Bug | [Androsmart]Get Auto Time: "b'0\\n'" has type str, but expected one of: int, bool | alexandra.farcasiu@randstaddigital.com | alexandra.farcasiu@randstaddigital.com | Integrated | 23-Jul-2024 07:36 | 03-Sep-2024 08:51 | Androsmart | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 1
MATRIX-82653 | Story | [gPTP] Study gPTP Requirements for SDV Architecture | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Closed | 22-Jul-2024 10:54 | 26-Aug-2024 08:15 | gPTP | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 0.75
MATRIX-82652 | Story | [gptp] Deep Dive into gPTP Specifications | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Closed | 22-Jul-2024 10:52 | 26-Aug-2024 08:15 | gPTP | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 6.75
MATRIX-82650 | Epic | Ramp-Up and Documentation of gPTP Protocol for New Team Members | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Closed | 22-Jul-2024 10:47 | 26-Aug-2024 08:16 | gPTP |  | 6.75
MATRIX-82645 | Story | Removing Warning Message (Failed to locate element after 6 scroll attempts. Errors encountered) from HTML logs | nageshwari.subbiah@rntbci.com | nageshwari.subbiah@rntbci.com | Closed | 17-Jul-2024 11:52 | 26-Aug-2024 10:06 | Appium | MATRIX_24.3.2_W32 | 0
MATRIX-82642 | Sub-task | [Androsmart Refactoring] Final Code Review and Clean-up: gRPC Error Code Implementation | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 17-Jul-2024 08:25 | 02-Aug-2024 15:57 | Androsmart | MATRIX_24.2.4_W25, MATRIX_24.3.1_W29, MATRIX_24.3.3_W35 | 0
MATRIX-82629 | Bug | [Androsmart]Exception calling application: [Errno 20] Not a directory on pull llk | alexandra.farcasiu@randstaddigital.com | alexandra.farcasiu@randstaddigital.com | Closed | 15-Jul-2024 08:25 | 03-Sep-2024 08:24 | Androsmart | MATRIX_24.3.3_W35 | 1
MATRIX-82453 | Bug | [LOGMON]DLT connection failure during Start Dlt Monitor (retrieval of files) | diego.fernandez3954@ctag.com | Eya.Abdelhedi@celadodc-rswl.com | In Progress | 12-Jul-2024 11:48 | 10-Sep-2024 10:19 | Logmon | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 6.25
MATRIX-82353 | Bug | [Logmon] DLT Monitor deletes the first 0 of the milliseconds when return an DLT trace information | andres.alfaya@ctag.com | andres.alfaya@ctag.com | Integrated | 11-Jul-2024 10:13 | 03-Sep-2024 08:51 | Logmon | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 0.5
MATRIX-82346 | Story | [Appium] Fix Logger Error: Python Logger Messages Displayed in Robot Framework Terminal | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Closed | 11-Jul-2024 08:24 | 26-Aug-2024 08:16 | Appium |  | 3
MATRIX-82300 | Story | [Matrix][Androsmart] Saving of service logs to file | jose.rivas3401@ctag.com | fred.ojo3685@ctag.com | Closed | 02-Jul-2024 06:38 | 28-Aug-2024 08:12 | Androsmart |  | 0
MATRIX-82263 | Bug | [Appium] Appium Crash with Matrix v10.5.3 in Full Campaign execution | vignesh.narayanasamy@rntbci.com | vignesh.narayanasamy@rntbci.com | Blocked | 27-Jun-2024 11:57 | 05-Sep-2024 14:25 | Appium | MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-81997 | Bug | [Matrix ] Scroll and swipe_by_coordinates , doesn't work for scroll_to_exact element function | ahlem.zouaoui@celadodc-rswl.com | ahlem.zouaoui@celadodc-rswl.com | Blocked | 12-Jun-2024 14:28 | 10-Sep-2024 12:49 | Appium | MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-81987 | Story | [RilShell] LLK to search available networks | daniel.varela4101@ctag.com | daniel.varela4101@ctag.com | In Progress | 11-Jun-2024 13:26 | 10-Sep-2024 13:06 | Services, Wicket | MATRIX_24.3.1_W29 | 3.5
MATRIX-81882 | Story | [gPTP] Add Client (Slave) Simulation Capability | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 30-May-2024 08:41 | 26-Aug-2024 08:17 | gPTP | MATRIX_24.3.3_W35 | 1
MATRIX-81881 | Story | [gPTP]Align Server Configuration Using JSON Files | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Implemented | 30-May-2024 08:34 | 08-Sep-2024 11:01 | gPTP | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 9.25
MATRIX-81879 | Epic | [gPTP] Refactor and Enhance gPTP Support for SDV in MATRIX | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | In Progress | 30-May-2024 08:29 | 03-Sep-2024 12:55 | gPTP |  | 15
MATRIX-81708 | Bug | RELIABILITY][APPIUM]Unable to create Appium driver, Appium Settings app is not running after 5000ms | anoob.aravindakshan@randstaddigital.com | anoob.aravindakshan@randstaddigital.com | Closed | 10-May-2024 10:17 | 06-Sep-2024 08:34 | Appium | MATRIX_24.2.3_W22, MATRIX_24.2.4_W25, MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 9.25
MATRIX-81707 | Bug | [RELIABILITY][APPIUM]Unable to create Appium driver, settings put global hidden_api_policy 1'' exited with code 20 | anoob.aravindakshan@randstaddigital.com | anoob.aravindakshan@randstaddigital.com | Closed | 10-May-2024 10:00 | 28-Aug-2024 05:34 | Appium | MATRIX_24.2.4_W25 | 0
MATRIX-81706 | Story | Requesting support for Appium Driver Creation purpose | rania.SOUISSI@CELADODC-RSWL.com | manel.mhiri@celadodc-rswl.com | Closed | 10-May-2024 09:17 | 26-Aug-2024 07:33 | Appium | MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 0
MATRIX-81685 | Epic | Move all matrix services and apis to poetry version 1.8.2 | guillaume.escoffre@ampere.cars | guillaume.escoffre@ampere.cars | Implemented | 06-May-2024 09:15 | 05-Sep-2024 12:42 | Framework |  | 7
MATRIX-81547 | Story | Remove asoundpylib | alexandru-rudi.matau@ampere.cars | wissem.MANSOURI@CELADODC-RSWL.com | Implemented | 24-Apr-2024 10:13 | 05-Sep-2024 14:12 | Framework, TKD | MATRIX_24.3.5_W41 | 1
MATRIX-81431 | Bug | Appium fails to select element via element id, even after the element is found | ranit.saha@randstaddigital.com | ranit.saha@randstaddigital.com | Implemented | 04-Apr-2024 13:23 | 05-Sep-2024 14:30 | Appium | MATRIX_24.2.2_W19, MATRIX_24.2.3_W22, MATRIX_24.2.4_W25, MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 9.25
MATRIX-81428 | Story | Move androsmart libraries to rfw_services/ivi in Matrix v11 | vernon.long@ampere.cars | rahma.haddar@celadodc-rswl.com | Implemented | 04-Apr-2024 08:22 | 10-Sep-2024 09:25 | Androsmart, Ivi_Test_Service | MATRIX_24.3.4_W38 | 3
MATRIX-81398 | Story | Implement handling of timeout on the gRPC server side | alexandru-rudi.matau@ampere.cars | Eya.Abdelhedi@celadodc-rswl.com | Implemented | 27-Mar-2024 09:31 | 10-Sep-2024 08:45 | Services | MATRIX_24.3.4_W38 | 8
MATRIX-81397 | Story | Implement global and per API/LLK timeout on the gRPC client side | alexandru-rudi.matau@ampere.cars | Eya.Abdelhedi@celadodc-rswl.com | Implemented | 27-Mar-2024 09:28 | 10-Sep-2024 08:45 | Services | MATRIX_24.3.1_W29, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 8
MATRIX-81385 | Story | Implement the proposal | vernon.long@ampere.cars | rahma.haddar@celadodc-rswl.com | Blocked | 26-Mar-2024 14:50 | 30-Aug-2024 14:48 | Architecture Config Benches, Canakin | MATRIX_24.3.3_W35, MATRIX_24.3.5_W41 | 0
MATRIX-81178 | Epic | [SOME/IP] Support SOMEIP E2E profil 4 for SDV | pierre.de-mauduit-du-plessis@ampere.cars | wissem.MANSOURI@CELADODC-RSWL.com | In Progress | 04-Mar-2024 13:48 | 05-Sep-2024 15:54 | Canakin | MATRIX_24.2.2_W19, MATRIX_24.2.3_W22, MATRIX_24.2.4_W25, MATRIX_24.3.1_W29, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 15
MATRIX-81129 | Epic | [SOME/IP] Implement Multicast_threshold mechanism | vernon.long@ampere.cars | rahma.haddar@celadodc-rswl.com | In Progress | 22-Feb-2024 17:32 | 27-Aug-2024 14:38 | Canakin |  | 12.5
MATRIX-80976 | Story | Adapt gitlab-ci.yaml to run through pipeline a training based on Outlinr icons with the new mechanism | helia.correia@ampere.cars | elyes.LABIDI@CELADODC-RSWL.com | In Progress | 09-Feb-2024 09:37 | 03-Sep-2024 13:58 | TKD | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 15
MATRIX-80918 | Bug | Investigate and fix demoCI job regarding RHL on top of KMR | guillaume.escoffre@ampere.cars | cyril.nivelle@ampere.cars | Blocked | 24-Jan-2024 16:39 | 03-Sep-2024 08:51 | Framework | MATRIX_24.1.1_W06, MATRIX_24.1.2_W09, MATRIX_24.1.3_W12, MATRIX_24.2.1_W16, MATRIX_24.2.2_W19, MATRIX_24.2.3_W22, MATRIX_24.2.4_W25, MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0
MATRIX-80826 | Story | [RilShell] LLK to change MNO | diego.vazquez3957@ctag.com | daniel.varela4101@ctag.com | In Progress | 11-Jan-2024 13:03 | 10-Sep-2024 13:07 | Services, Wicket | MATRIX_24.3.1_W29 | 3.5
MATRIX-79753 | Bug | [MATRIX][PCAP] Losing info of UDS packet when it is segmented in more than one TCP segment | rodrigo.sifontes3955@ctag.com | alexandru-rudi.matau@ampere.cars | Blocked | 20-Nov-2023 15:17 | 03-Sep-2024 08:51 | Logmon | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0.5
MATRIX-79617 | Epic | [FWK] Evaluate supporting gRPC Deadlines | alexandru-rudi.matau@ampere.cars | Eya.Abdelhedi@celadodc-rswl.com | Implemented | 15-Nov-2023 11:06 | 30-Aug-2024 13:51 | Canakin, Cirrus, Logmon, Wicket | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 13
MATRIX-79608 | Epic | [Logging] Refactor Logmon handling of purely offline monitor classes | alexandru-rudi.matau@ampere.cars | pius-xavier.felix-xavier@rntbci.com | Integrated | 10-Nov-2023 18:57 | 05-Sep-2024 12:43 | Logmon | MATRIX_24.2.4_W25, MATRIX_24.3.3_W35 | 0
MATRIX-77928 | Story | Automatic pipeline Trig when outliner is updated | guillaume.escoffre@ampere.cars | elyes.LABIDI@CELADODC-RSWL.com | In Progress | 15-Jun-2023 09:06 | 03-Sep-2024 13:58 | Framework | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 15
MATRIX-74436 | Story | [CTAG] Working on the pipeline and bench intro for IVI only | cyril.nivelle@ampere.cars | vernon.long@ampere.cars | Ready | 30-Mar-2023 09:32 | 03-Sep-2024 08:51 | Services | SAT_23.2.1_W16, SAT_23.2.2_W19, SAT_23.2.3_W22, SAT_23.2.4_W25, SAT_23.3.1_W29, MATRIX_23.4.2_W48, MATRIX_23.4.3_W51, MATRIX_23.4.4_W02 | 0
MATRIX-74435 | Story | [CTAG] Working on the pipeline and bench intro for IVC only | cyril.nivelle@ampere.cars | vernon.long@ampere.cars | Ready | 30-Mar-2023 09:10 | 03-Sep-2024 08:51 | Services | SAT_23.2.2_W19, SAT_23.2.3_W22, SAT_23.2.4_W25, SAT_23.3.1_W29, MATRIX_23.4.3_W51, MATRIX_23.4.4_W02 | 0
CCSEXT-159491 | Task | Enable App crawler | nicolas.conte-extern@renault.com | Eya.Abdelhedi@celadodc-rswl.com | In Review | 15-Jan-2024 15:06 | 26-Aug-2024 07:56 | HMI-Delivery | HMI PI21 Sprint 1, HMI PI21 Sprint 2, HMI PI21 Sprint 3, HMI PI21 Sprint 4, HMI PI22 Sprint 1, HMI PI22 Sprint 2, HMI PI22 Sprint 3, HMI PI22 Sprint 4, HMI PI23 Sprint 1, HMI PI23 Sprint 2, HMI PI23 Sprint 3 | 0
CCSEXT-148612 | Task | Test module plugin - E2E Testings in dedicated test modules of the repo | nicolas.conte-extern@renault.com | Eya.Abdelhedi@celadodc-rswl.com | Implemented | 04-Oct-2023 15:02 | 14-Aug-2024 15:43 | HMI-Delivery | HMI PI20 Sprint 3, HMI PI20 Sprint 4 | 0