## Sheet1
Issue Key | Issue Type | Summary | Reporter | Assignee | Status | Created | Updated | Component/s | Sprint | consumed Story Points
MATRIX-83425 | Sub-task | [gPTP] Add feature to create macvlan interface for ecu simulation. | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Implemented | 22-Aug-2024 08:15 | 08-Sep-2024 11:01 | gPTP | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 5
MATRIX-83423 | Story | [TKD] Align tkd service | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Implemented | 20-Aug-2024 15:31 | 11-Sep-2024 14:22 | TKD | MATRIX_24.3.4_W38 | 1.25
MATRIX-83422 | Story | [TKD] align tkd_api | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Implemented | 20-Aug-2024 15:31 | 11-Sep-2024 14:22 | TKD |  | 1
MATRIX-83290 | Story | [FWK] Study and Evaluation of gRPC Deadlines Implementation for MATRIX Services | wissem.MANSOURI@CELADODC-RSWL.com | Eya.Abdelhedi@celadodc-rswl.com | Implemented | 09-Aug-2024 08:32 | 23-Sep-2024 08:08 | Framework |  | 3.75
MATRIX-83228 | Story | [SOME/IP - SDV] use same json format as vsomeip library for E2E Profile 4 | laurent.josse@ampere.cars | wissem.MANSOURI@CELADODC-RSWL.com | Implemented | 08-Aug-2024 07:03 | 13-Sep-2024 09:59 | Canakin | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 1.5
MATRIX-83227 | Story | [SOME/IP - SDV] Implement E2E Profile 4 to be compatible with vsomeip library | laurent.josse@ampere.cars | laurent.josse@ampere.cars | Implemented | 08-Aug-2024 06:40 | 24-Sep-2024 06:21 | Canakin | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 4.75
MATRIX-83217 | Story | Move all MATRIX APIs to poetry 1.8.2 | alexandru-rudi.matau@ampere.cars | rahma.haddar@celadodc-rswl.com | Integrated | 05-Aug-2024 09:45 | 05-Sep-2024 12:42 | Services |  | 0.75
MATRIX-83081 | Sub-task | [Androsmart Refactoring] Review and Clean-up Client side | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Closed | 02-Aug-2024 15:55 | 19-Aug-2024 08:27 | Androsmart | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 5
MATRIX-83080 | Sub-task | [Androsmart Refactoring] Review and Clean-up on Server side | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Closed | 02-Aug-2024 15:55 | 19-Aug-2024 08:27 | Androsmart | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 5.5
MATRIX-83079 | Story | [Androsmart Refactoring] Review and Clean-up: gRPC Error Code Implementation | wissem.MANSOURI@CELADODC-RSWL.com | rahma.haddar@celadodc-rswl.com | Closed | 02-Aug-2024 15:54 | 26-Aug-2024 08:15 | Androsmart | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 5
MATRIX-82677 | Story | [Token Handler] Enhance Token Configuration for JFrog and Poetry in MATRIX Service | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | In Progress | 29-Jul-2024 14:31 | 12-Sep-2024 11:21 | Framework | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 15
MATRIX-82672 | Story | Taking more than 40 secs while taping on a element available in the media player | ashrin.femina-extern@rntbci.com | ashrin.femina-extern@rntbci.com | In Progress | 29-Jul-2024 04:59 | 20-Sep-2024 12:10 | Appium |  | 4.75
MATRIX-82661 | Bug | [Androsmart]Get Auto Time: "b'0\\n'" has type str, but expected one of: int, bool | alexandra.farcasiu@randstaddigital.com | alexandra.farcasiu@randstaddigital.com | Integrated | 23-Jul-2024 07:36 | 03-Sep-2024 08:51 | Androsmart | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 1
MATRIX-82653 | Story | [gPTP] Study gPTP Requirements for SDV Architecture | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Closed | 22-Jul-2024 10:54 | 26-Aug-2024 08:15 | gPTP | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 0.75
MATRIX-82652 | Story | [gptp] Deep Dive into gPTP Specifications | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Closed | 22-Jul-2024 10:52 | 26-Aug-2024 08:15 | gPTP | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 7
MATRIX-82629 | Bug | [Androsmart]Exception calling application: [Errno 20] Not a directory on pull llk | alexandra.farcasiu@randstaddigital.com | alexandra.farcasiu@randstaddigital.com | Closed | 15-Jul-2024 08:25 | 03-Sep-2024 08:24 | Androsmart | MATRIX_24.3.3_W35 | 0.5
MATRIX-82453 | Bug | [LOGMON]DLT connection failure during Start Dlt Monitor (retrieval of files) | diego.fernandez3954@ctag.com | Eya.Abdelhedi@celadodc-rswl.com | In Progress | 12-Jul-2024 11:48 | 23-Sep-2024 08:12 | Logmon | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 6
MATRIX-82353 | Bug | [Logmon] DLT Monitor deletes the first 0 of the milliseconds when return an DLT trace information | andres.alfaya@ctag.com | andres.alfaya@ctag.com | Integrated | 11-Jul-2024 10:13 | 03-Sep-2024 08:51 | Logmon | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 0.75
MATRIX-82346 | Story | [Appium] Fix Logger Error: Python Logger Messages Displayed in Robot Framework Terminal | wissem.MANSOURI@CELADODC-RSWL.com | houcem.jouini@celadodc-rswl.com | Closed | 11-Jul-2024 08:24 | 26-Aug-2024 08:16 | Appium |  | 2
MATRIX-81987 | Story | [RilShell] LLK to search available networks | daniel.varela4101@ctag.com | daniel.varela4101@ctag.com | In Progress | 11-Jun-2024 13:26 | 20-Sep-2024 10:54 | Services, Wicket | MATRIX_24.3.1_W29 | 0.25
MATRIX-81882 | Story | [gPTP] Add Client (Slave) Simulation Capability | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Closed | 30-May-2024 08:41 | 26-Aug-2024 08:17 | gPTP | MATRIX_24.3.3_W35 | 2.25
MATRIX-81881 | Story | [gPTP]Align Server Configuration Using JSON Files | wissem.MANSOURI@CELADODC-RSWL.com | wissem.MANSOURI@CELADODC-RSWL.com | Implemented | 30-May-2024 08:34 | 16-Sep-2024 07:15 | gPTP | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 3.5
MATRIX-81708 | Bug | RELIABILITY][APPIUM]Unable to create Appium driver, Appium Settings app is not running after 5000ms | anoob.aravindakshan@randstaddigital.com | anoob.aravindakshan@randstaddigital.com | Closed | 10-May-2024 10:17 | 06-Sep-2024 08:34 | Appium | MATRIX_24.2.3_W22, MATRIX_24.2.4_W25, MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35 | 9.5
MATRIX-81547 | Story | Remove asoundpylib | alexandru-rudi.matau@ampere.cars | wissem.MANSOURI@CELADODC-RSWL.com | Implemented | 24-Apr-2024 10:13 | 05-Sep-2024 14:12 | Framework, TKD | MATRIX_24.3.5_W41 | 0.75
MATRIX-81431 | Bug | Appium fails to select element via element id, even after the element is found | ranit.saha@randstaddigital.com | ranit.saha@randstaddigital.com | Implemented | 04-Apr-2024 13:23 | 23-Sep-2024 11:51 | Appium | MATRIX_24.2.2_W19, MATRIX_24.2.3_W22, MATRIX_24.2.4_W25, MATRIX_24.3.1_W29, MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 9.25
MATRIX-81428 | Story | Move androsmart libraries to rfw_services/ivi in Matrix v11 | vernon.long@ampere.cars | rahma.haddar@celadodc-rswl.com | Implemented | 04-Apr-2024 08:22 | 18-Sep-2024 07:57 | Androsmart, Ivi_Test_Service | MATRIX_24.3.4_W38 | 3
MATRIX-81398 | Story | Implement handling of timeout on the gRPC server side | alexandru-rudi.matau@ampere.cars | guillaume.escoffre@ampere.cars | Implemented | 27-Mar-2024 09:31 | 23-Sep-2024 08:12 | Services | MATRIX_24.3.4_W38 | 8
MATRIX-81397 | Story | Implement global and per API/LLK timeout on the gRPC client side | alexandru-rudi.matau@ampere.cars | Eya.Abdelhedi@celadodc-rswl.com | Implemented | 27-Mar-2024 09:28 | 23-Sep-2024 15:38 | Services | MATRIX_24.3.1_W29, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 8
MATRIX-80976 | Story | Adapt gitlab-ci.yaml to run through pipeline a training based on Outlinr icons with the new mechanism | helia.correia@ampere.cars | elyes.LABIDI@CELADODC-RSWL.com | In Progress | 09-Feb-2024 09:37 | 19-Sep-2024 14:13 | TKD | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 15
MATRIX-80826 | Story | [RilShell] LLK to change MNO | diego.vazquez3957@ctag.com | daniel.varela4101@ctag.com | In Progress | 11-Jan-2024 13:03 | 20-Sep-2024 10:54 | Services, Wicket | MATRIX_24.3.1_W29 | 0.25
MATRIX-79753 | Bug | [MATRIX][PCAP] Losing info of UDS packet when it is segmented in more than one TCP segment | rodrigo.sifontes3955@ctag.com | alexandru-rudi.matau@ampere.cars | Blocked | 20-Nov-2023 15:17 | 23-Sep-2024 08:12 | Logmon | MATRIX_24.3.2_W32, MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 0.5
MATRIX-77928 | Story | Automatic pipeline Trig when outliner is updated | guillaume.escoffre@ampere.cars | elyes.LABIDI@CELADODC-RSWL.com | In Progress | 15-Jun-2023 09:06 | 23-Sep-2024 08:12 | Framework | MATRIX_24.3.3_W35, MATRIX_24.3.4_W38 | 15